## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi |  |  | 40% |  | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi |  |  | 50% |  | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% | 31.82% | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi |  |  | 30% |  | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% | 40% | 0% | No new substations completed. Delay in electrical components impacts schedule.

## Dashboard
Metroville Urban Rail Expansion Project Dashboard
| Display here main numbers/KPI of the overall project |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Phase 1
[5 empty] | Phase 2 | [6 empty] | ←Illustrative
Phase 3
Phase 4
PHASE 1
| Progress - Completion % | [8 empty] | Project Financials
| Status Update |  | Challenges
| List the main achievements |  | - Eastern section in risk - Delay due to rocky terrain - 6mi behind schedule ACTION: in progress evaluation of alternative method to expedite progress. - Overspent in the excavation ACTION: Savings on materials have offset this, keeping us within 5% of our overall budget projection for this phase. - Substations construction: Delay in electrical components ACTION: action plan in progress with Buyer
| Community Feedback Highlights |  |  | Relevant Risks
Insert positive feedback
Insert concerning feedback
Add electrification progress
Add budget tracking